## Sheet1
Project Name: Anti-Ragging Portal
Module : Parent
|  |  | Overall Defect Summary |  |  | Verification Summary |  |  | Segregation
|  |  | Completed | 4 |  | Completed | 0 |  | Development |  | 0
|  |  | Deffered | 0 |  | Pending | 0 |  | GD |  | 0
|  |  | Incomplete | 0 |  |  |  |  | ID |  | 0
|  |  | In Progress | 0 |  |  |  |  | Marketing |  | 0
|  |  | Not Applicable | 0 |  |  |  |  | QA |  | 0
|  |  | Not Started | 0 |  |  |  |  | Others |  | 4
|  |  | Pending | 0
|  |  | Rejected | 0
|  |  | Total | 4
Date | No | Change ID | Description | Origin | Modification to be made | Type | Department | Author | Submitted To | Status | Severity | Priority | Verified | Comments / Feedback | Screen Shots
30/07/2019 | 1 |  | The admin must be able to login. with authentic username and password | Parent | If admin is try to login with unauthorised username and password then the invalid credentials message will display. | Incorrect Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 2 |  | The admin must be able to login. with authentic username and password | Parent | If adminis able to login with authorised username and password then the admin can go through feedback section ,complain section and contact section. | correct Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 3 |  | the user is able to register by providing all required details. | Parent | If user is try to register with not providing all required details then message will diplay to fill required details. | Incorrect Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 4 |  | the user is able to register by providing all required details. | Parent | If user is try to register with providing all required details then user is successfully registered and user will allocated with unique tracking ID. | correct Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 5 |  | the user should provide 10 digits contact number | Parent | If user will not provide 10 digits then it will display message to fill detail in the requested format. | Incorrect Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 6 |  | the user should provide 10 digits contact number | Parent | If user will provide 10 digits then request will forward. | correct Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 7 |  | the user is able to track their complain by using their tracking ID | Parent | the user is able to track their complain if they provide correct tracking ID and then they can see the status of their complain | correct Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 8 |  | the user is able to track their complain by using their tracking ID | Parent | the user is unable to track their complain if they provide incorrect tracking ID and then they cannot see the status of their complain | Incorrect Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 9 |  | watch vedio button will forward request to the youtube | Parent | the user is able to see the vedios realted to anti-ragging. | correct Functionality | others | Mamta | centum | completed | Low | Low
30/07/2019 | 10 |  | the user is able to give feedback . | Parent | the user is able to give feedback by providing all required details. | correct Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 11 |  | the user is able to give feedback . | Parent | the user is unable to give feedback if he/she not provide all required details. | Incorrect Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 12 |  | the user is able to contact the admin. | Parent | the user is able to conatct the admin if he/she will provide all required details. | correct Functionality | others | Mamta | centum | completed | Meduim | Meduim
30/07/2019 | 13 |  | the user is able to contact the admin. | Parent | the user is unable to conatct the admin if he/she will not provide all required details. | Incorrect Functionality | others | Mamta | centum | completed | Meduim | Meduim